## Sheet1
# | Task Name | Duration | Start | Finish | Resource Name | Note
| SOFA Project | 75 | 2021-04-01 | 28/4/2021
1 | Prepare for project | 1 | 2021-04-01 | 2021-04-01 |  | Select PM, determine role of member
2 | Initiating phase | 4 | 2021-05-01 | 2021-08-01 |  | List up requirement, define scope
3 | Project Plan phase | 5 | 2021-11-01 | 15/1/2021 |  | Create project plan management
4 | Executing phase | 60 | 18/1/2021 | 16/4/2021
4.1 | Design | 12 | 18/1/2021 | 2021-02-02
4.1.1 | Create usecase description | 2 | 18/1/2021 | 19/1/2021
4.1.2 | Create architechture design | 2 | 20/1/2021 | 21/1/2021
4.1.3 | Create database design | 1 | 22/1/2021 | 22/1/2021
4.1.4 | GUI design | 5 | 25/1/2021 | 29/1/2021
4.1.5 | Create SRS and Software design description | 2 | 2021-01-02 | 2021-02-02
4.2 | Implementation | 39 | 22/2/2021 | 16/4/2021
4.2.1 | Backend | 10 | 22/2/2021 | 2021-05-03
4.2.1 | Frontend | 20 | 2021-08-03 | 2021-02-04
4.2.1.1 | SOFA (Android) | 20 | 2021-08-03 | 2021-02-04
4.2.1.2 | SOFA Manager (Website) | 10 | 22/3/2021 | 2021-02-04
4.3 | Test | 9 | 2021-05-04 | 15/4/2021
4.4 | Create test document | 1 | 16/4/2021 | 16/4/2021
5 | Close project | 8 | 19/4/2021 | 28/4/2021
5.1 | Create user guide document | 1 | 19/4/2021 | 19/4/2021
5.2 | Modify all document | 4 | 20/4/2021 | 23/4/2021
5.3 | Create final report | 2 | 26/4/2021 | 27/4/2021
5.4 | Close project | 1 | 28/4/2021 | 28/4/2021

## Sheet2
# | Task Name | Duration | Start | Finish | Resource Name | Note
I | SOFA Project | 75 | 2021-04-01 | 28/4/2021
1 | Pre-Initiating Phase | 1 | 2021-04-01 | 2021-04-01
1.1 | Select Project Manager | 1 | 2021-04-01 | 2021-04-01 | All member
1.2 | Determine the role of team member | 1 | 2021-04-01 | 2021-04-01 | All member
1.3 | Choose topic | 1 | 2021-04-01 | 2021-04-01 | All member
2 | Initiating phase | 4 | 2021-05-01 | 2021-08-01
2.1 | List up requirment | 1 | 2021-05-01 | 2021-05-01 | HoangNH
2.2 | Define scope of project | 1 | 2021-06-01 | 2021-06-01 | All member
2.3 | Create report 1 - project introduction document | 1 | 2021-07-01 | 2021-07-01 | All member
2.4 | Modify project introduction document | 1 | 2021-08-01 | 2021-08-01 | HoangNH
3 | Project Plan Phase | 5 | 2021-11-01 | 15/1/2021
3.1 | Choose working model process | 1 | 2021-11-01 | 2021-11-01 | VanLT
3.2 | Select tools and techniques | 1 | 2021-11-01 | 2021-11-01 | TungNT
3.3 | Create project schedule | 1 | 2021-12-01 | 2021-12-01 | VanLT
3.4 | Create risk management plan | 1 | 13/1/2021 | 13/1/2021 | VienMV
3.5 | Oganize project resources | 1 | 14/1/2021 | 14/1/2021 | VanLT
3.6 | Create report 2 - software project management plan | 1 | 15/1/2021 | 15/1/2021 | VanLT
4 | Executing Phase | 60 | 18/1/2021 | 16/4/2021
4.1 | Design | 12 | 18/1/2021 | 2021-02-02
4.1.1 | List up use case | 0.5 | 18/1/2021 | 18/1/2021 | All member
4.1.2 | Create use case description | 1.5 | 18/1/2021 | 19/1/2021 | All member
4.1.3 | Create report 3 -Software requirment specification | 3 | 20/1/2021 | 22/1/2021 | HoangNH
4.1.4 | Create Architechture design | 2 | 20/1/2021 | 21/1/2021
4.1.4.1 | Data Architechture design | 1 | 20/1/2021 | 20/1/2021 | VienMV
4.1.4.2 | Data flow architectures | 1 | 20/1/2021 | 20/1/2021 | TungNT
4.1.4.3 | Call and Return architectures | 0.5 | 21/1/2021 | 21/1/2021 | VanLT
4.1.4.4 | Object Oriented architecture | 0.5 | 21/1/2021 | 21/1/2021 | VanLT
4.1.4.5 | Layered architecture | 2 | 20/1/2021 | 21/1/2021 | DungHV
4.1.5 | Database design | 1 | 22/1/2021 | 22/1/2021 | VienMV
4.1.6 | GUI layout design | 5 | 25/1/2021 | 29/1/2021 | DungHV
4.1.7 | Create report 4 - Software design | 3 | 31/1/2021 | 2021-02-02 | HoangNH
4.2 | Implementation | 13 | 22/2/2021 | 16/4/2021
4.2.1 | Back-end (RESTful API) | 10 | 22/2/2021 | 2021-05-03
4.2.1.1 | Configuration and setup environment | 1 | 22/2/2021 | 22/2/2021 | VanLT
4.2.1.2 | Create database | 1 | 23/2/2021 | 23/2/2021 | VienMV
4.2.1.3 | Coding common, Middleware, DBContext | 1 | 23/2/2021 | 23/2/2021 | VanLT
4.2.1.4 | Coding Model and Data Access Object | 2 | 24/2/2021 | 25/2/2021 | All member
4.2.1.5 | Coding controller handler request of manager page | 5 | 25/2/2021 | 2021-04-03 | All member
4.2.1.6 | Coding controller handler request of user app | 1 | 2021-04-03 | 2021-05-03 | TungNT
4.2.2 | Front-end | 20 | 2021-08-03 | 2021-02-04
4.2.2.1 | SOFA Manager (Web flatform) | 10 | 22/3/2021 | 2021-02-04 | TungNT
4.2.2.2 | SOFA (Android app flatform) | 20 | 2021-08-03 | 2021-02-04 | All member
4.2.3 | Deploy
4.2.3.1 | Deploy host and domain config | 1 | 2021-02-04 | 2021-02-04 | VanLT
4.3 | Test | 9 | 2021-05-04 | 15/4/2021
4.3.1 | Create all testcase | 2 | 2021-05-04 | 2021-06-04 | VienMV
4.3.2 | Implementation test | 4 | 2021-07-04 | 2021-12-04 | All member
4.3.4 | Verify test | 1 | 13/4/2021 | 13/4/2021 | VienMV
4.3.5 | Fix bug and retest | 2 | 13/4/2021 | 15/4/2021 | All member
4.3.3 | Sumary and evaluation | 0.5 | 16/4/2021 | 16/4/2021 | VienMV
4.1.9 | Create report 5 - Test case document | 0.5 | 16/4/2021 | 16/4/2021 | VienMV
4.4 | Finish executing phase
5 | Close | 8 | 19/4/2021 | 28/4/2021
5.1 | Create report 6 - Software user guide | 1 | 19/4/2021 | 19/4/2021
5.2 | Create final report | 2 | 26/4/2021 | 27/4/2021
5.3 | Project complete | 1 | 28/4/2021 | 28/4/2021