## Sheet1
# | WBS Item | Complexity | Est. Effort (Man-days)
I | SOFA Project |  | 375
1 | Pre-Initiating Phase |  | 5
1.1 | Select Project Manager | Simple | 1 | Simple
1.2 | Determine the role of team member | Simple | 1 | Medium
1.3 | Choose topic | Simple | 2 | Complex
1.4 | Register capstone project | Simple | 1
2 | Initiating phase |  | 0
2.1 | Determine stakeholder | Medium
2.2 | List up requirment | Simple
2.3 | Define scope of project | Simple
2.4 | Create report 1 - project introduction document | Medium
2.6 | Modify project introduction document | Simple
3 | Project Plan Phase |  | 0
3.1 | Choose working model process | Simple
3.2 | Select tools and techniques | Simple
3.3 | Create project schedule | Simple
3.4 | Create risk management plan | Medium
3.5 | Oganize project resources | Simple
3.6 | Create report 2 - software project management plan | Medium
4 | Executing Phase |  | 0
4.1 | Design |  | 0
4.1.1 | List up use case | Simple
4.1.2 | Create use case description | Medium
4.1.3 | Create report 3 -Software requirment specification | Medium
4.1.4 | Create Architechture design | Complex
4.1.4.1 | Data Architechture design | Medium
4.1.4.2 | Data flow architectures | Medium
4.1.4.3 | Call and Return architectures | Medium
4.1.4.4 | Object Oriented architecture | Medium
4.1.4.5 | Layered architecture | Medium
4.1.5 | Database design | Medium
4.1.6 | GUI layout design | Complex
4.1.7 | Create report 4 - Software design | Simple
4.1.8 | Redesign use case | Simple
4.2 | Implementation |  | 0
4.2.1 | Back-end (RESTful API) |  | 0
4.2.1.1 | Configuration and setup environment
4.2.1.2 | Create database
4.2.1.3 | Coding common, Middleware, DBContext
4.2.1.4 | Coding Model and Data Access Object
4.2.1.5 | Coding controller handler request of manager page
4.2.1.6 | Coding controller handler request of user app
4.2.2 | Front-end |  | 0
4.2.2.1 | SOFA Manager (Web flatform)
4.2.2.2 | SOFA (Android app flatform)
4.2.3 | Deploy |  | 0
4.2.3.1 | Deploy host and domain config
4.3 | Test |  | 0
4.3.1 | Test manager website |  | 0
4.3.1.1 | Create test cases for unit test
4.3.1.2 | Unit test
4.3.1.3 | Fix bug
4.3.1.4 | Create test cases for intergration test
4.3.1.5 | Intergration test
4.3.1.6 | Fix bug
4.3.1.7 | Create test cases for system test
4.3.1.8 | System test
4.3.1.9 | Fix bug
4.3.1.10 | Create test case for acceptance test
4.3.1.11 | Acceptance test
4.3.1.12 | Fix bug
4.3.2 | Test user application |  | 0
4.3.2.1 | Create test cases for unit test
4.3.2.2 | Unit test
4.3.2.3 | Fix bug
4.3.2.4 | Create test cases for intergration test
4.3.2.5 | Intergration test
4.3.2.6 | Fix bug
4.3.2.7 | Create test cases for system test
4.3.2.8 | System test
4.3.2.9 | Fix bug
4.3.2.10 | Create test case for acceptance test
4.3.2.11 | Acceptance test
4.3.2.12 | Fix bug
4.3.3 | Sumary and evaluation
4.1.9 | Create report 5 - Test case document | Simple
4.1.10 | Create report 6 - Software user guide | Simple
4.4 | Finish executing phase |  | 0
5 | Monitoring and controlling |  | 0
5.1 | Progress report
6 | Close |  | 0
6.1 | Create final report
6.2 | Prepare for final presentation
6.3 | Present final prject
6.4 | Project complete